## Sheet1
UI Testing Bug Report
Bug ID | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Screenshot
Bug_001 | Skip Button Not Working on Onboarding Screens | The "Skip" button on the onboarding screens does not respond to user interaction. Although the screens can be skipped by swiping left, tapping the "Skip" button has no effect. This issue occurs consistently on the first, and second onboarding screens. | 1. Install and launch the APK 2. Observe the first onboarding screen 3. Tap the "skip" button 4. Repeat the same on the second onboarding screens | Tapping the "Skip" button should immediately navigate the user to the main app or homepage. | Nothing happens when the "Skip" button is tapped. The user can only proceed by swiping manually | Major | P2 | Fixed | Bug_ID_001.jpeg Onboarding_Screen.mp4
Bug_002 | App Closes When Back Button is Pressed After Login | After successful login, pressing the back button causes the app to close instead of taking the user back to the previous screen (e.g., home or dashboard). This breaks expected navigation flow. | 1. Launch APK 2. Go to Login screen 3. Enter log in 4. On the next screen, press the Android back button | User should be taken back to login screen or receive a "Press back again to exit" prompt | The app closes immediately | Critical | P0 | Fixed | Bug_ID_002.png App Exit.mp4
Bug_003 | "Add New Card" Screen Missing in APK | In Figma design, there is a screen for adding a new payment card. However, this screen is completely missing in the current APK build. The user has no way to add a payment card, breaking the expected payment flow. | 1. Launch APK 2. Navigate to the payment details 3. Look for the “Add New Card” Option 4. Compare with Figma 5. In Payment Method, "Add new Card" is not clickable | User should see the “Add New Card” Text as per Figma and be able to enter card details | Screen is missing entirely; the feature to add a card does not exist | Major | P1 | Fixed | Bug_ID_003.png
Bug_004 | Side Menu (with Personal Details) Missing in APK | In the Figma design, there is a side menu that includes the user's personal details (name, email, profile image, etc.). This screen is entirely missing in the APK. Tapping on the menu icon does not reveal any side navigation or related content. | 1. Open Figma and navigate to the screen containing the side menu 2. Observe the design and contents of the side navigation panel 3. Launch the APK 4. Tap the menu icon or try to open the side menu | A side menu should slide out or appear, showing personal user details as shown in the Figma design | No side menu appears in the APK. feature is completely missing | Major | P1 | Fixed | Figma screen Recording.mp4 APK Recordings.mp4
Bug_005 | App Exits on Back Button Press Instead of Going Back to the Previous Screen | In many screens throughout the app, pressing the Android back button does not return the user to the previous screen. Instead, the app closes immediately, which breaks the natural navigation flow. | 1. Launch the APK 2. Navigate to any screen (e.g., Event Details, Profile, Map) 3. Press the Android back button 4. Observe what happens | The app should return to the previous screen or show a confirmation before exiting (e.g., “Press back again to exit”) | The app exits immediately, even when not on the main screen. | Critical | P0 | Fixed | Bug_ID_005.png APK Exit.mp4
Bug_006 | Duplicate Event Entries in Past Events (APK vs. Figma) | In the Figma design, the "Past Events" section displays a variety of unique events, each with different names, images, and details. In the APK, however, One event is repeated multiple times, making the section look incomplete and not useful for users. | 1. Open Figma and go to the Past Events page 2. Look at the "Past Events" section (multiple distinct events shown) 3. Launch the APK 4. Go to the same section and observe that only one event is repeated | The "Past Events" section should show a variety of actual past events, just like in the Figma design | One event is repeated multiple times Instead of showing different event data. | Minor | P2 | Fixed | Bug_ID_006.jpeg
Bug_007 | “Bookmarks” Screen Missing in Side Menu – Not Available in APK | In the Figma design, the side menu contains multiple navigation options, including Bookmarks, Contact, and Settings. The Bookmarks screen is a full, dedicated screen where saved items or events are listed. In the current APK build, this entire Bookmarks screen is missing — The menu item is not present at all. | 1. Open Figma → Go to Side Menu design 2. Click or review “Bookmarks” section (a separate full screen) 3. Launch the APK 4. Try to open the side menu not available 5. Bookmarks is not available | The user should be able to tap on “Bookmarks” from the side menu and navigate to a screen showing saved items | The bookmarks screen does not exist in the APK — the menu bar is missing. | Major | P1 | Fixed | Bug_ID_007.png
Bug_008 | Message Screen is available in Figma but missing in APK | The Figma design includes a dedicated Message screen that likely allows users to view conversations . However, this screen is completely missing in the APK. | 1. Open the Figma file 2. Locate and review the Message screen 3. Open the APK 4. Try to access the Message feature via any navigation or menu 5. Observe that it is not available in the APK | The user should be able to access the Message screen from the UI as designed in Figma | Message Screen is not available in APK | Minor | P2 | Fixed | Bug_ID_008.png
Bug_009 | Calendar Screen is present in Figma but missing in APK | The Calendar screen is designed and available in the Figma flow, likely meant to explore new events. However, this screen is not available in the current APK — there is no navigation to the calendar view, nor any display of calendar-based event filtering. | 1. Open Figma and navigate to the Calendar screen 2. Observe its design and placement in the flow 3. Open the APK 4. Open the Calendar screen via any menu or navigation 5. Confirm it is not present | Calendar screen should be implemented and accessible, allowing users to view events based on dates | Calendar screen is missing from APK | Minor | P2 | Fixed | Bug_ID_009.png
Bug_010 | Event Screen is present in Figma but missing in APK | The Event screen is designed and available in the Figma flow. However, this screen is not available in the current APK | 1. Open Figma and check the event screen in Flow 1 2. Observe its design and place it in flow 3. Open the APK 4. Check for the Event Screen: Upcoming and Past events screens are available, and the events screen is missing | The events screen should be implemented and accessible allowing the user to see the events apart from the upcoming and past events. | The events screen is missing in APK | Minor | P2 | Rejected | Bug_ID_010.png
Bug_011 | Sign out Pop-up missing in APK | Sign Out popup missing in APK but available in Figma | 1. Open Figma, look for the sign-out pop-up. 1. Launch the app 2. Try to access the Profile section from the navigation or settings 3. Tap on Sign Out | - The user should be able to open the Profile section as shown in Figma. - Inside the Profile, when clicking on Sign Out, a confirmation pop-up should appear (e.g., “Do you want to sign out?”). | The signout pop-up is missing in APK | Major | P1 | Fixed | Signout Pop-up.png

## Sheet2
|  |  |  | UI Testing Bug Report |  |  | Priority
Bug ID | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | P2 | Status | Screenshot
Bug_UI_001 | Dummy Text Appears on Onboarding Screens in APK | The onboarding screens in both Figma and the APK contains dummy text ("Lorem ipsum..."). This indicates that the final content is not yet provide,d and the app may go live with Incomplete copy. | 1. Open Figma → Check onboarding screen text 2. Launch APK →Navigate to the onboarding screens 3. Oberve that the same dummy text is used | Finalized, meaningful onboarding content should be present in both design and APK | "Lorem ipsum..." placeholder text is used in both design and implementation | Minor | P2 | Pending | Bug_ID_001.jpeg
Bug_UI_002 | Map Page Search Text Mismatch (Figma vs APK) | The placeholder text in the map screen's search bar is inconsistent. In Figma, it says "Search for new address", but in the APK it shows Find for events". This creates confusion and affects content accuracy. | 1. Open the Figma design → Navigate to the map screen 2. Check the placeholder text in the search bar 3. Launch the APK → Go to the same map screen 4. Compare the text in the search bar | Placeholder text should match Figma: "Search for new address" | APK shows: "Finds for events" | Minor | P2 | Pending | Bug_UI_002.png
Bug_UI_003 | Minor color mismatch between Figma and APK UI | Some UI elements (e.g., background, buttons, text, icons) have slightly different colors in the APK compared to the original Figma design. | 1. Open Figma design 2. Identify and note the specific color codes used (e.g., button fill color, text color) 3. Launch the APK 4. Navigate to the corresponding screens and compare the UI element colors 5. Confirm visible differences in color tones. | All the Color in the APK should match excately Figma | APK use slightly color tones | Minor | P2 | Fixed | Bug_UI_001.png
Bug_UI_004 | Filter Page Spelling Mistake Figma and APK | In the Filter page, Spelling is found in the location Textfield | 1. Open the Figma design 2. Look for the Filter page and check the spelling mistake (e.g, Malayssia ) | The spelling will be malaysia | The spelling is malayssia | Minor | P2 | Pending | Bug_UI_04.png